## Overview
Foundation of Goodness — Food & Education Distributions (Dec 2025 – Feb 2026)
Metric | Value | Note
FOOD — dry-ration packs
Packs distributed (official total) | 12578 | Target was 10,000 — exceeded
Sum of weekly totals | 12577 | Weekly table adds to 12,577 (1 less than the stated total)
Villages covered | 330
Sum of area-level entries (as listed) | 16713 | Higher than 12,578 — the report lists some deliveries twice (weekly table + photo caption). Treat area totals as upper bounds.
EDUCATION — Essential School Supply Packs (ESSP)
ESSP requests (island-wide) | 7475
ESSP packs received | 4075
ESSP packs distributed (as of 3 Feb 2026) | 3720
ESSP packs pending hand-out | 355 | Received − distributed
Requests still unmet | 3755 | Requests − distributed
Students listed by school | 3569 | Schools named in the report; the rest of the 3,720 were not itemised
Cost per ESSP pack (Rs.) | 5400 | USD 18 per pack; no admin cost deducted
Value of packs distributed (Rs.) | 20088000

## Food - Weekly
Period | Packs
Week 1 (1st week of Dec 2025) | 1136
Week 2 (2nd week of Dec 2025) | 2986
Week 3 (3rd week of Dec 2025) | 3811
Week 4 | 2468
Week 5 | 1210
Week 6 (pending distribution) | 966
TOTAL | 12577
Report states 12,578 in total.

## Food - All Deliveries
Area | Province (as in report) | District | Packs | When | Note
Badulla 2 | Uva | Badulla | 600 | 13 Dec 2025
Badulla 1 – Hali-Ela DS Division | Uva | Badulla | 399 | 9 Dec 2025
Mihindumpitiya / Lunugala – 1 | Uva | Badulla | 420 | Wk 5&6
Kandaketiya | Uva | Badulla | 352 | 18 Dec 2025
Jaffna | Northern | Jaffna | 310 | 11–12 Dec 2025
Nuwara Eliya (Kothmale & N.Eliya) | Central | Nuwara Eliya | 356 | Multiple | Kothmale 250 may repeat the separate 'Kothmale' row
Nuwara Eliya (Kothmale & N.Eliya) | Central | Nuwara Eliya | 250 | Multiple | Kothmale 250 may repeat the separate 'Kothmale' row
Passara | Uva | Badulla | 436 | Wk 5&6
Mihindumpitiya / Lunugala – 2 | Uva | Badulla | 240 | Wk 5&6
Chavakachcheri | Northern | Jaffna | 300 | Wk 5&6
Palavi, Wanathawilluwa & Madurankuliya | North Western | Puttalam | 250 | 10 Dec 2025
Mannar | Northern | Mannar | 250 | 10 & 18 Dec 2025
Mannar | Northern | Mannar | 200 | Wk 5&6
Pallai | Northern | Kilinochchi | 200 | Wk 1–3
Pallai | Northern | Kilinochchi | 235 | Wk 1–3
Pallai | Northern | Kilinochchi | 200 | Wk 1–3
Pallai | Northern | Kilinochchi | 200 | Wk 1–3
Oddusuddan | Northern | Mullaitivu | 150 | Wk 1
Oddusuddan | Northern | Mullaitivu | 235 | Wk 3
Thirukkovil | Eastern | Ampara | 200 | Wk 3 | Wk3 + dated entry may be the same delivery
Thirukkovil | Eastern | Ampara | 200 | 19 Dec 2025 | Wk3 + dated entry may be the same delivery
Hatton (incl. Hatton/N.Eliya) | Central | Nuwara Eliya | 150 | 12–13 Dec 2025
Hatton (incl. Hatton/N.Eliya) | Central | Nuwara Eliya | 169 | 24 Dec 2025
Dambulla (incl. Laggala) | Central | Matale | 150 | Multiple
Dambulla (incl. Laggala) | Central | Matale | 50 | Multiple
Dambulla (incl. Laggala) | Central | Matale | 150 | Multiple
Bandarawela | Uva | Badulla | 103 | Wk 1
Bandarawela | Uva | Badulla | 100 | Wk 3
Bandarawela | Uva | Badulla | 100 | 19 Dec 2025
Nawalapitiya | Central | Kandy | 150 | 18 Dec 2025
Nawalapitiya | Central | Kandy | 100 | Wk 3
Nuwara Eliya & Welimada | Central/Uva | Nuwara Eliya / Badulla | 85 | 13 Dec 2025 | Spans two districts
Nuwara Eliya & Welimada | Central/Uva | Nuwara Eliya / Badulla | 234 | 23 Dec 2025 | Spans two districts
Angoda | Western | Colombo | 125 | 13 Dec 2025
Ja-Ela / Makawita | Western | Gampaha | 125 | 12 Dec 2025 | Also 1,000 water
Ja-Ela / Makawita | Western | Gampaha | 125 | Wk 2 | Also 1,000 water
Ja-Ela / Makawita | Western | Gampaha | 130 | 23 Dec 2025 | Also 1,000 water
Halmulla, Wellampitiya | Western | Colombo | 125 | 13 Dec 2025 | Wk + dated entry may be the same delivery
Halmulla, Wellampitiya | Western | Colombo | 125 | Wk 2 | Wk + dated entry may be the same delivery
Gampola | Central | Kandy | 150 | Wk 1
Gampola | Central | Kandy | 122 | Wk 2
Dehiattakandiya | Eastern | Ampara | 128 | 13 Dec 2025
Polonnaruwa (incl. Sinharajapura, Onegama) | North Central | Polonnaruwa | 100 | 4 Dec 2025 | Onegama 120 may repeat the 'Onagama' row
Polonnaruwa (incl. Sinharajapura, Onegama) | North Central | Polonnaruwa | 120 | 18 Dec 2025 | Onegama 120 may repeat the 'Onagama' row
Polonnaruwa (incl. Sinharajapura, Onegama) | North Central | Polonnaruwa | 100 | 24 Dec 2025 | Onegama 120 may repeat the 'Onagama' row
Ratnapura | Sabaragamuwa | Ratnapura | 150 | Wk 1
Cheddikulam | Northern | Vavuniya | 150 | Wk 1
Trincomalee (incl. Pulmude, Seruwila) | Eastern | Trincomalee | 100 | Multiple
Trincomalee (incl. Pulmude, Seruwila) | Eastern | Trincomalee | 76 | Multiple
Trincomalee (incl. Pulmude, Seruwila) | Eastern | Trincomalee | 100 | Multiple
Trincomalee (incl. Pulmude, Seruwila) | Eastern | Trincomalee | 21 | Multiple
Batticaloa | Eastern | Batticaloa | 100 | Wk 2
Batticaloa | Eastern | Batticaloa | 300 | 23 Dec 2025
Vavuniya | Northern | Vavuniya | 100 | 17 Dec 2025
Vavuniya | Northern | Vavuniya | 250 | 29 Dec 2025
Mahiyanganaya | Uva | Badulla | 100 | Wk 2 | Wk3 + dated entry may be the same delivery
Mahiyanganaya | Uva | Badulla | 121 | Wk 3 | Wk3 + dated entry may be the same delivery
Mahiyanganaya | Uva | Badulla | 121 | 12 Dec 2025 | Wk3 + dated entry may be the same delivery
Hasalaka (incl. Udaththawa) | Central | Kandy | 100 | Wk 1
Hasalaka (incl. Udaththawa) | Central | Kandy | 150 | Wk 5&6
Kottikawatta | Western | Colombo | 100 | Wk 2 | Wk + dated entry may be the same delivery
Kottikawatta | Western | Colombo | 100 | 13 Dec 2025 | Wk + dated entry may be the same delivery
Pemaduwa – Anuradhapura | North Central/Western | Anuradhapura | 100 | Wk 2 | Wk + dated entry may be the same delivery
Pemaduwa – Anuradhapura | North Central/Western | Anuradhapura | 100 | 13 Dec 2025 | Wk + dated entry may be the same delivery
Sittandy | Eastern | Batticaloa | 100 | Wk 3 | Wk + dated entry may be the same delivery
Sittandy | Eastern | Batticaloa | 100 | 18 Dec 2025 | Wk + dated entry may be the same delivery
Ridigama | North Western | Kurunegala | 100 | Wk 3 | Wk + dated entry may be the same delivery
Ridigama | North Western | Kurunegala | 100 | 18 Dec 2025 | Wk + dated entry may be the same delivery
Madurankuliya, Puttalam | North Western | Puttalam | 150 | Wk 3 | Wk + dated entry may be the same delivery
Madurankuliya, Puttalam | North Western | Puttalam | 150 | 17 Dec 2025 | Wk + dated entry may be the same delivery
Kankuveli | Eastern | Trincomalee | 200 | Wk 3
Katharagama | — | Monaragala | 105 | 24 Dec 2025
Ambathale & Mulleriyawa | Western | Colombo | 125 | Wk 2
Ambathale & Mulleriyawa | Western | Colombo | 150 | 9 Dec 2025
Ankumbura, Karagahapitiya – Kandy | Central | Kandy | 114 | Wk 3 | Wk + dated entry may be the same delivery
Ankumbura, Karagahapitiya – Kandy | Central | Kandy | 114 | 18 Dec 2025 | Wk + dated entry may be the same delivery
Pahathahewahata & Kundasale | Central | Kandy | 170 | Wk 3 | Wk + dated entry may be the same delivery
Pahathahewahata & Kundasale | Central | Kandy | 170 | 18 Dec 2025 | Wk + dated entry may be the same delivery
Rikillagaskada – Hanguranketa | Central | Nuwara Eliya | 51 | Wk 3 | Wk3 + dated entry may be the same delivery
Rikillagaskada – Hanguranketa | Central | Nuwara Eliya | 51 | 18 Dec 2025 | Wk3 + dated entry may be the same delivery
Rikillagaskada – Hanguranketa | Central | Nuwara Eliya | 135 | Wk 5&6 | Wk3 + dated entry may be the same delivery
Kothmale | Central | Nuwara Eliya | 250 | Wk 3 | May repeat Kothmale 250 above
Giriulla – Kurunegala | North Western | Kurunegala | 95 | Wk 3 | Wk + dated entry may be the same delivery
Giriulla – Kurunegala | North Western | Kurunegala | 95 | 18 Dec 2025 | Wk + dated entry may be the same delivery
Onagama – Polonnaruwa | North Central | Polonnaruwa | 120 | Wk 3 | May repeat Onegama 120 above
Suriya Foundation – Welimada | Uva | Badulla | 80 | Wk 3
Muttur Relief Camp | Eastern | Trincomalee | 120 | Wk 3
Mathagal | Northern | Jaffna | 150 | Wk 3
Kandy – Pahathahewahata | Central | Kandy | 170 | Wk 3 | May repeat Pahathahewahata 170 above
Yatawara – Wattegama / Kandy | Central | Kandy | 35 | Wk 3 | Wk + dated entry may be the same delivery
Yatawara – Wattegama / Kandy | Central | Kandy | 35 | 17 Dec 2025 | Wk + dated entry may be the same delivery
Galaha | Central | Kandy | 150 | Wk 1
Maskeliya | Central | Nuwara Eliya | 76 | Wk 1
Maskeliya | Central | Nuwara Eliya | 50 | 19 Dec 2025
Monaragala | Uva | Monaragala | 47 | 9 Dec 2025 | Small delivery – follow up
Mulleriya | Western | Colombo | 25 | Wk 2 | Small delivery – follow up
Kolonnawa / Salamulla | Western | Colombo | 15 | Wk 2 | Small delivery – follow up
Kolonnawa / Salamulla | Western | Colombo | 15 | 13 Dec 2025 | Small delivery – follow up
Nagahawela – Kotikawatta | Western | Colombo | 130 | Wk 5&6
Fonseka Maniyo – Kotikawatta | Western | Colombo | 12 | Wk 5&6 | Small delivery – follow up
Ududumbara, Hunnasgiriya, Kandy | Central | Kandy | 150 | 29 Dec 2025
Meegahakiwula & Soranathota | Central (report) / Uva | Badulla | 355 | 26 Dec 2025 | Both places are in Badulla district
Uhana, Ampara | Eastern | Ampara | 50 | 25 Dec 2025
Moragolla Village, Badulla | Uva | Badulla | 126 | 19 & 25 Dec 2025 | Also 40 water cases, 35 mattresses / non-food items
Soranathota / Haliella / Badulla DS Division | Uva | Badulla | 339 | Wk 2 | May overlap Badulla 1/2 rows
Soranathota / Haliella / Badulla DS Division | Uva | Badulla | 335 | Wk 2 | May overlap Badulla 1/2 rows
Soranathota / Haliella / Badulla DS Division | Uva | Badulla | 265 | Wk 2 | May overlap Badulla 1/2 rows
|  | TOTAL (as listed) | 16713
Yellow = may be the same delivery listed twice in the report. Orange = fewer than 50 packs (report suggests follow-up).

## Food - By Area
Rank | Area | District | Total packs | No. of deliveries | Need signal
1 | Soranathota / Haliella / Badulla DS Division | Badulla | 939 | 3 | Acute (300+ in one delivery)
2 | Pallai | Kilinochchi | 835 | 4 | Recurring (2+ deliveries)
3 | Nuwara Eliya (Kothmale & N.Eliya) | Nuwara Eliya | 606 | 2 | Acute (300+ in one delivery)
4 | Badulla 2 | Badulla | 600 | 1 | Acute (300+ in one delivery)
5 | Mannar | Mannar | 450 | 2 | Recurring (2+ deliveries)
6 | Passara | Badulla | 436 | 1 | Acute (300+ in one delivery)
7 | Mihindumpitiya / Lunugala – 1 | Badulla | 420 | 1 | Acute (300+ in one delivery)
8 | Thirukkovil | Ampara | 400 | 2 | Recurring (2+ deliveries)
9 | Batticaloa | Batticaloa | 400 | 2 | Acute (300+ in one delivery)
10 | Badulla 1 – Hali-Ela DS Division | Badulla | 399 | 1 | Acute (300+ in one delivery)
11 | Oddusuddan | Mullaitivu | 385 | 2 | Recurring (2+ deliveries)
12 | Ja-Ela / Makawita | Gampaha | 380 | 3 | Recurring (2+ deliveries)
13 | Meegahakiwula & Soranathota | Badulla | 355 | 1 | Acute (300+ in one delivery)
14 | Kandaketiya | Badulla | 352 | 1 | Acute (300+ in one delivery)
15 | Dambulla (incl. Laggala) | Matale | 350 | 3 | Recurring (2+ deliveries)
16 | Vavuniya | Vavuniya | 350 | 2 | Recurring (2+ deliveries)
17 | Mahiyanganaya | Badulla | 342 | 3 | Recurring (2+ deliveries)
18 | Pahathahewahata & Kundasale | Kandy | 340 | 2 | Recurring (2+ deliveries)
19 | Polonnaruwa (incl. Sinharajapura, Onegama) | Polonnaruwa | 320 | 3 | Recurring (2+ deliveries)
20 | Hatton (incl. Hatton/N.Eliya) | Nuwara Eliya | 319 | 2 | Recurring (2+ deliveries)
21 | Nuwara Eliya & Welimada | Nuwara Eliya / Badulla | 319 | 2 | Recurring (2+ deliveries)
22 | Jaffna | Jaffna | 310 | 1 | Acute (300+ in one delivery)
23 | Bandarawela | Badulla | 303 | 3 | Recurring (2+ deliveries)
24 | Chavakachcheri | Jaffna | 300 | 1 | Acute (300+ in one delivery)
25 | Madurankuliya, Puttalam | Puttalam | 300 | 2 | Recurring (2+ deliveries)
26 | Trincomalee (incl. Pulmude, Seruwila) | Trincomalee | 297 | 4 | Recurring (2+ deliveries)
27 | Ambathale & Mulleriyawa | Colombo | 275 | 2 | Recurring (2+ deliveries)
28 | Gampola | Kandy | 272 | 2 | Recurring (2+ deliveries)
29 | Palavi, Wanathawilluwa & Madurankuliya | Puttalam | 250 | 1
30 | Nawalapitiya | Kandy | 250 | 2 | Recurring (2+ deliveries)
31 | Halmulla, Wellampitiya | Colombo | 250 | 2 | Recurring (2+ deliveries)
32 | Hasalaka (incl. Udaththawa) | Kandy | 250 | 2 | Recurring (2+ deliveries)
33 | Kothmale | Nuwara Eliya | 250 | 1
34 | Mihindumpitiya / Lunugala – 2 | Badulla | 240 | 1
35 | Rikillagaskada – Hanguranketa | Nuwara Eliya | 237 | 3 | Recurring (2+ deliveries)
36 | Ankumbura, Karagahapitiya – Kandy | Kandy | 228 | 2 | Recurring (2+ deliveries)
37 | Kottikawatta | Colombo | 200 | 2 | Recurring (2+ deliveries)
38 | Pemaduwa – Anuradhapura | Anuradhapura | 200 | 2 | Recurring (2+ deliveries)
39 | Sittandy | Batticaloa | 200 | 2 | Recurring (2+ deliveries)
40 | Ridigama | Kurunegala | 200 | 2 | Recurring (2+ deliveries)
41 | Kankuveli | Trincomalee | 200 | 1
42 | Giriulla – Kurunegala | Kurunegala | 190 | 2 | Recurring (2+ deliveries)
43 | Kandy – Pahathahewahata | Kandy | 170 | 1
44 | Ratnapura | Ratnapura | 150 | 1
45 | Cheddikulam | Vavuniya | 150 | 1
46 | Mathagal | Jaffna | 150 | 1
47 | Galaha | Kandy | 150 | 1
48 | Ududumbara, Hunnasgiriya, Kandy | Kandy | 150 | 1
49 | Nagahawela – Kotikawatta | Colombo | 130 | 1
50 | Dehiattakandiya | Ampara | 128 | 1
51 | Maskeliya | Nuwara Eliya | 126 | 2 | Recurring (2+ deliveries)
52 | Moragolla Village, Badulla | Badulla | 126 | 1
53 | Angoda | Colombo | 125 | 1
54 | Onagama – Polonnaruwa | Polonnaruwa | 120 | 1
55 | Muttur Relief Camp | Trincomalee | 120 | 1
56 | Katharagama | Monaragala | 105 | 1
57 | Suriya Foundation – Welimada | Badulla | 80 | 1
58 | Yatawara – Wattegama / Kandy | Kandy | 70 | 2 | Recurring (2+ deliveries)
59 | Uhana, Ampara | Ampara | 50 | 1
60 | Monaragala | Monaragala | 47 | 1 | Small — follow up
61 | Kolonnawa / Salamulla | Colombo | 30 | 2 | Recurring (2+ deliveries)
62 | Mulleriya | Colombo | 25 | 1 | Small — follow up
63 | Fonseka Maniyo – Kotikawatta | Colombo | 12 | 1 | Small — follow up

## Education - How ESSP Works
How Foundation of Goodness gives education support
Each child receives one Essential School Supply Pack (ESSP), requested through their school or as an individual request from a struggling student.
Item in each pack | Qty per child | Purpose
School bag | 1 | Carry books to school
Exercise books | 8 | Writing books for the school term
Pens | 2 | Writing
Shoe voucher | 1 | Redeemed for a pair of school shoes
Cost per pack (Rs.) | 5400
Cost per pack (USD) | 18
Admin cost deducted | None
Delivery channel |  | Mostly school-by-school distributions (whole class/school), plus individual requests from struggling students (e.g. Seenigama, Kolonnawa, island-wide).

## Education - Schools
Rank | School / Centre | District | Students (packs) | School bags | Exercise books | Pens | Shoe vouchers | Pack value (Rs.)
1 | Mawadavila Maliyadewam Maha Vidyalaya | Galle | 375 | 375 | 3000 | 750 | 375 | 2025000
2 | Minhaj Maha Vidyalaya – Nikagolla | Matale | 348 | 348 | 2784 | 696 | 348 | 1879200
3 | Thambalawewa Primary School | Polonnaruwa | 282 | 282 | 2256 | 564 | 282 | 1522800
4 | Bt/Vinayagar Kiramam Alaimagal Vidyalayam | Batticaloa | 270 | 270 | 2160 | 540 | 270 | 1458000
5 | Kn/Mukkompan Maha Vidyalayam – Pallai | Kilinochchi | 260 | 260 | 2080 | 520 | 260 | 1404000
6 | J/Columbuthurai Hindu Maha Vidyalayam | Jaffna | 252 | 252 | 2016 | 504 | 252 | 1360800
7 | Tk/Mandanai Tamil Mixed School | Ampara | 247 | 247 | 1976 | 494 | 247 | 1333800
8 | Sudharmarama Dhamma School | Ratnapura | 192 | 192 | 1536 | 384 | 192 | 1036800
9 | B/Kukulapola Kanishta Vidyalaya | Badulla | 167 | 167 | 1336 | 334 | 167 | 901800
10 | Uppalawatta Junior School | Puttalam | 150 | 150 | 1200 | 300 | 150 | 810000
11 | Yatawatta Nandana Vidyalaya | Matale | 150 | 150 | 1200 | 300 | 150 | 810000
12 | Kincora Tamil Vidyalayam | Nuwara Eliya | 100 | 100 | 800 | 200 | 100 | 540000
13 | Pathana Sawbhagya Model School | Galle | 96 | 96 | 768 | 192 | 96 | 518400
14 | Mu/Eeswaran Vidyalayam | Mullaitivu | 91 | 91 | 728 | 182 | 91 | 491400
15 | Requests from struggling students (island-wide) | Island-wide | 75 | 75 | 600 | 150 | 75 | 405000
16 | CP/KOT/Delunthalamada Vidyalaya | Nuwara Eliya | 72 | 72 | 576 | 144 | 72 | 388800
17 | Thotagamuwa Vijayabha Primary School | Galle | 70 | 70 | 560 | 140 | 70 | 378000
18 | CP/KOT/Gankewela Vidyalaya | Nuwara Eliya | 50 | 50 | 400 | 100 | 50 | 270000
19 | Kalukunnammaduwa Vidyalaya | Vavuniya | 41 | 41 | 328 | 82 | 41 | 221400
20 | Patuwatha Kimbissa Primary School | Matale | 37 | 37 | 296 | 74 | 37 | 199800
21 | Piyawara Pre School | Vavuniya | 35 | 35 | 280 | 70 | 35 | 189000
22 | Eppala Junior School – Udugama | Galle | 35 | 35 | 280 | 70 | 35 | 189000
23 | Navodya Primary School – Walewala | Matale | 34 | 34 | 272 | 68 | 34 | 183600
24 | Lahiru Pre School | Galle | 30 | 30 | 240 | 60 | 30 | 162000
25 | Galkeminawa Thilaka Junior School | Galle | 30 | 30 | 240 | 60 | 30 | 162000
26 | Hithgoda Walpola Junior School | Kandy | 30 | 30 | 240 | 60 | 30 | 162000
27 | Church of the Ascension Day Care Centre | Badulla | 25 | 25 | 200 | 50 | 25 | 135000
28 | Requests from struggling students – Seenigama | Galle | 22 | 22 | 176 | 44 | 22 | 118800
29 | Requests from struggling students – Kolonnawa | Colombo | 3 | 3 | 24 | 6 | 3 | 16200
| TOTAL |  | 3569 | 3569 | 28552 | 7138 | 3569 | 19272600

## By District - Coverage vs Need
District | Food packs (as listed) | Food deliveries | Food insecure households 2024 (WFP %) | Food: gap flag | ESSP students | Schools / centres | Education priority rank (1 = most need) | Education: gap flag
Ampara | 578 | 4 | 18.4 |  | 247 | 1 | 20
Anuradhapura | 200 | 2 | 12.8 |  | 0 | 0 | 11 | No ESSP yet
Badulla | 4592 | 18 | 16.5 |  | 192 | 2 | 5
Batticaloa | 600 | 4 | 22.7 |  | 270 | 1 | 6
Colombo | 1047 | 12 | 6.7 |  | 3 | 1 | 22
Galle | 0 | 0 | 16.1 | No food packs yet | 658 | 7 | 25
Gampaha | 380 | 3 | 14.9 |  | 0 | 0 | 18 | No ESSP yet
Hambantota | 0 | 0 | 11.9 | No food packs yet | 0 | 0 | 15 | No ESSP yet
Jaffna | 760 | 3 | 15.4 |  | 252 | 1 | 17
Kalutara | 0 | 0 | 12.4 | No food packs yet | 0 | 0 | 19 | No ESSP yet
Kandy | 1880 | 15 | 8.7 |  | 30 | 1 | 9 | High need, low coverage
Kegalle | 0 | 0 | 8.6 | No food packs yet | 0 | 0 | 23 | No ESSP yet
Kilinochchi | 835 | 4 | 29 |  | 260 | 1 | 13
Kurunegala | 390 | 4 | 17.9 |  | 0 | 0 | 14 | No ESSP yet
Mannar | 450 | 2 | 28.9 | High need, low coverage | 0 | 0 | 10 | High need, low coverage
Matale | 350 | 3 | 21.2 | High need, low coverage | 569 | 4 | 16
Matara | 0 | 0 | 15.7 | No food packs yet | 0 | 0 | 24 | No ESSP yet
Monaragala | 152 | 2 | 21.6 | High need, low coverage | 0 | 0 | 3 | High need, low coverage
Mullaitivu | 385 | 2 | 29.3 | High need, low coverage | 91 | 1 | 21
Nuwara Eliya | 1538 | 10 | 27.5 |  | 222 | 3 | 1
Polonnaruwa | 440 | 4 | 15.2 |  | 282 | 1 | 8
Puttalam | 550 | 3 | 18.6 |  | 150 | 1 | 2
Ratnapura | 150 | 1 | 26.2 | High need, low coverage | 192 | 1 | 4
Trincomalee | 617 | 6 | 20.3 |  | 0 | 0 | 12 | No ESSP yet
Vavuniya | 500 | 3 | 27.2 |  | 76 | 2 | 7 | High need, low coverage
Also: "Nuwara Eliya / Badulla" (shared delivery) and "Island-wide" ESSP requests are not in any single district row.
Gap flag: food = WFP food insecurity ≥ 20% but < 500 packs; education = top-10 education priority but < 150 ESSP students.
Need data: WFP food insecurity map 2024; education priority from the Education Needs workbook (MPI 2019 + O/L 2024).